Version 1.02 May 2019

Procurement Portal

Timescale tracker – Public Contracts Regulations 2015

This document sets out key timescales relating to the main contract award procedures under the Public Contracts Regulations 2015.

The overriding requirement when setting timescales is to allow sufficient time for suppliers to prepare appropriate responses, taking account of the subject of the proposed contract, the contract award procedure to be used and the need, for example, for site visits. The table below sets out the minimum permitted timescales and the maximum permitted reductions. You must also take into consideration the general rules around setting of time limits that are set out at Regulation 47 of the Public Contracts Regulations 2015.

An appropriate time period will also need to be allocated for other aspects of the procurement process, e.g. evaluation of tender responses.

© 2015 Mills & Reeve LLP. You may use the content of this document provided that you accept that Mills & Reeve LLP excludes any and all liability whatsoever and howsoever arising resulting from any use of the content of this document to the fullest extent permissible by law.

Minimum timescales:

| Choice of procedure and stage | Standard timescales | Option for Member States relating to sub-central contracting authorities | Tenders submitted electronically | Requirement is urgent and longer time limit is impractical as a result | PIN published no more than 12 months and no less than 35 days from despatch of contract notice |
| --- | --- | --- | --- | --- | --- |
| Open |  |  |  |  |  |
| Despatch of contract notice to receipt of responses | 35 days |  | 5 day reduction | Period reduced to 15 days | Period reduced to 15 days |
| Standstill | 10 days |  |  |  |  |
| Restricted |  |  |  |  |  |
| Despatch of contract notice to receipt of responses | 30 days |  |  | Period reduced to 15 days |  |
| ITT to receipt of bids | 30 days | May agree time-limit with tenderers – in absence of agreement minimum period is 10 days | 5 day reduction | Period reduced to 10 days | Period reduced to 10 days |
| Standstill | 10 days |  |  |  |  |

| Choice of procedure and stage | Standard timescales | Option for Member States relating to sub-central contracting authorities | Tenders submitted electronically | Requirement is urgent and longer time limit is impractical as a result | PIN published no more than 12 months and no less than 35 days from despatch of contract notice |
| --- | --- | --- | --- | --- | --- |
| Competitive with Negotiation |  |  |  |  |  |
| Despatch of contract notice to expressions of interest | 30 days |  |  | Period reduced to15 days |  |
| ITN to receipt of initial tenders | 30 days | May agree time-limit with tenderers – in absence of agreement minimum period is 10 days | 5 day reduction | Period reduced to 10 days | Period reduced to 10 days |
| Standstill | 10 days |  |  |  |  |
| Competitive Dialogue |  |  |  |  |  |
| Despatch of contract notice to expressions of interest | 30 days |  |  |  |  |
| Standstill | 10 days |  |  |  |  |
| Innovation Partnership |  |  |  |  |  |
| Despatch of contract notice to expressions of interest | 30 days |  |  |  |  |
| Standstill | 10 days |  |  |  |  |